## Slide 1
Drink well.
Leave better.
San Diego's safe night out program
Scan at any partner bar for a safe ride home.
drinkwellleavebetter.com
IN PARTNERSHIP WITH UBER | LYFT | SD SAFETY | CA OTS

## Slide 2
Agenda
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS
01
The Problem
Why San Diego needs a new approach to DUI prevention
02
Our Solution
15 self-service breathalyzer kiosks at decision points
03
Project Methodology
Stakeholder analysis, WBS, phases & risk planning
04
Financial Strategy
Budget, revenue model & investor return
05
Risk & Mitigation
Key risks and contingency plans
06
Recommendations
Key findings and next steps

## Slide 3
SCANNING...
Drink well.
Leave better.
Smart kiosk technology that
encourages safe ride decisions
at San Diego's top venues.
Face-scan check-in
Instant ride booking
DUI prevention tech
Real-time data capture
Powered by
SafeNight SD
15 kiosk locations
across San Diego's
top bar districts.
15
Kiosk locations
3.75%
Cost of 1 DUI
21×
Minimum ROI
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS

## Slide 4
The Problem
WHY SAN DIEGO NEEDS A NEW APPROACH
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS
2,100+
DUI arrests annually
in San Diego County
$487M
Annual economic cost
medical, legal & lost productivity
30%
Of crashes alcohol-related
preventable with intervention
The gap in the system
Problem - Current DUI prevention relies on enforcement after the fact — arrests, fines, and tragedies. There is no infrastructure that intervenes at the decision point: when someone is leaving a bar and deciding whether to drive.
Every hour that passes without an intervention infrastructure costs San Diego approximately $55,600 in DUI-related economic damage.

## Slide 5
Our Solution
BEHAVIORAL INTERVENTION AT THE MOMENT OF DECISION · 15 SELF-SERVICE KIOSKS
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS
Behavioral economics in action: 15 kiosks at bar exits, transit hubs, and entertainment districts modify the choice environment at the moment of decision — real-time BAC feedback converts impaired intent into a safe ride home.
🍺
Bar Exits
Gaslamp, North Park, Pacific Beach — posted at departure points
🚌
Transit Centers
Downtown stations, trolley stops, bus terminals
🎉
Entertainment Districts
Event venues, stadiums, concert halls
How It Works
1
Patron approaches kiosk
Single-use breathalyzer mouthpiece — results in under 10 seconds
2
BAC result displayed
Clear color-coded output: green (safe), amber (caution), red (do not drive)
3
Rideshare option presented
QR code links directly to Uber/Lyft app with co-branded promo code
4
Data captured anonymously
Usage, BAC ranges, and rideshare conversions logged for KPI reporting

## Slide 7
Project Plan & Methodology
5 PHASES · 9-MONTH PILOT · KPI-DRIVEN EVALUATION · BEHAVIORAL ECONOMICS FRAMEWORK
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS
1
Vendor Procurement
RFP, select, contract
Month 1
2
Site Development
Identify locations, finalize agreements
Month 2
3
Install & Deploy
All 15 units operational
Month 3
4
Pilot Operations
Training, launch marketing, monitor performance
Months 4–9
5
Evaluation
Analyze data, measure results
Month 9
Key Performance Indicators
25+
BAC tests/kiosk/day
95%+
Device uptime
>0.5mi
Rideshare pickup radius
100%
Data collection rate

## Slide 8
Kiosk Pilot Program — Project Timeline
Apr 2026 — Apr 2027
◆ CRITICAL PATH
May '26
Jun '26
Jul '26
Aug '26
Sep '26
Oct '26
Nov '26
Dec '26
Jan '27
Feb '27
Mar '27
Apr '27
Task
Start
End
PHASE 1 — VENDOR PROCUREMENT
▶ Develop & Issue RFP
4/27
5/1
▶ Vendor Review Period
5/4
5/15
▶ Bid Evaluation & Scoring
5/18
5/22
▶ Compliance Verification
5/25
5/29
▶ Vendor Selection & Award
6/1
6/1
◆ ★ Vendor Selected
6/1
6/1
▶ Contract Negotiation
6/2
6/8
PHASE 2 — SITE DEVELOPMENT
Candidate Location Scoring
5/4
5/15
▶ Physical Site Walkthroughs
5/18
5/29
Venue Outreach & MOU Drafting
6/1
6/26
▶ MOU Review & Negotiation
6/29
7/10
▶ Finalize 15 Signed MOUs
7/13
7/13
◆ ★ All MOUs Signed
7/13
7/13
PHASE 3 — INSTALLATION & DEPLOYMENT
▶ Equipment Delivery
7/14
7/20
▶ Install Units 1–5
7/21
7/27
▶ Install Units 6–10
7/28
8/3
▶ Install Units 11–15
8/4
8/10
▶ Connectivity & Function Check
8/11
8/17
◆ ★ All Kiosks Operational
8/17
8/17
PHASE 4 — PILOT OPERATIONS
▶ Venue Staff Training
8/18
8/31
Marketing Materials Design
5/4
5/22
Signage Deployment
5/25
6/5
◆ ★ Awareness Campaign Launch
8/31
8/31
Rideshare Partnership Outreach
5/4
6/12
▶ Kiosk Operations & Monitoring
9/1
3/1
PHASE 5 — EVALUATION
▶ Weekly Data Quality Checks
8/18
2/15
DUI Baseline Data Request
5/4
5/29
Mid-Pilot KPI Review
11/17
11/23
▶ Final Data Aggregation
3/2
3/29
▶ Final Report Compilation
3/30
4/26
◆ ★ Final Report Delivered
4/26
4/26
Procurement
Site Dev
Installation
Operations
Evaluation
Critical Path
Today
drinkwellleavebetter.com
Critical path = tasks with zero float that control project end date
Apr 23, 2026

## Slide 9
WBS Milestones & Acceptance Criteria
STRUCTURED DELIVERABLES · MEASURABLE ACCEPTANCE CRITERIA · 9-MONTH TIMELINE
Milestone
Target Date
Acceptance Criteria
Vendor Selected
Month 1
Vendor meets cost, compliance, and data-capability targets; contract executed
15 Site MOUs Signed
Month 2
All 15 venue agreements fully executed; site walkthroughs confirmed
All Kiosks Operational
Month 3
100% unit functionality confirmed across all locations; connectivity verified
Awareness Campaign Live
Month 3
Marketing materials deployed at all 15 sites; rideshare promo codes active
Pilot Monitoring Complete
Month 9
Six-month data collected consistently; 95%+ device uptime maintained
Final Evaluation Report
Month 9
KPI analysis delivered to sponsor; DUI baseline delta documented
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS

## Slide 10
Stakeholder Analysis
POWER · INTEREST · PRIORITY · KEY CONCERN
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS
Stakeholder
Type
Power
Interest
Priority
Key Concern / Cadence
Project Sponsor
Internal
95%
90%
HIGH
Budget efficiency & pilot success | Weekly
Venue Owners
Internal/Ext
80%
85%
HIGH
Liability reduction & customer safety | Weekly
Operations Team
Internal
85%
95%
HIGH
System uptime & data quality | Weekly
Safety Advocates
External
50%
90%
MED
Public safety outcomes | Monthly
Rideshare Providers
External
55%
70%
MED
Increased demand signals | Monthly
Public Health Orgs
External
40%
65%
MON
Behavioral intervention data | Quarterly

## Slide 11
Financial Strategy
THE INVESTMENT CASE — COSTS · REVENUE · RETURN
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS
Total Investment
$65,000 / year
15 kiosks × $3,500 installation & maintenance
$52,500
Part-time coordinator (recommended)
$12,500
Revenue Streams
$432K est.
Kiosk screen advertising (15 kiosks)
$180,000
Government grants (CA OTS / NHTSA)
$150,000
B2B data licensing
$60,000
Bar venue subscriptions (SaaS)
$35,880
Rideshare referral commissions
$7,000
Estimated Year 1 Net Profit
$367,880
after all operating costs · 5.7× revenue-to-cost ratio
Social ROI by Scenario
Conservative
1 fatal DUI prevented
$1.4M
21× ROI
Realistic
3 incidents prevented
$4.2M
64× ROI
Optimistic
10 incidents prevented
$14M+
215× ROI
Investor Breakeven
Bar owners (liability avoidance)
Week 1
Corporate / brand sponsors
Immediate
Govt / grant funders
Month 1–2
Uber / Lyft rideshare
Month 2–3

## Slide 12
Risk Analysis
KEY RISKS · LIKELIHOOD · MITIGATION
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS
Risk
Likelihood
Impact
Owner
Mitigation
Vendor Delays
Medium
High
Procurement Lead
Secondary vendor shortlist; 2 backups pre-qualified during RFP phase.
Venue Withdrawal
Low-Med
Medium
Partnership Lead
Maintain 5 alternate backup locations; flexible MOU exit clauses.
Low Public Adoption
Medium
High
Marketing Lead
Pre-launch awareness campaign; rideshare promo codes as incentive.
Equipment Malfunction
Medium
High
Operations Lead
Vendor SLA with 48-hr response; spare units held in inventory.

## Slide 13
Quality Plan & Evaluation Standards
DEVICE UPTIME · DATA INTEGRITY · VENDOR COMPLIANCE · SCALABLE EVALUATION
01
Device Uptime Target
95% uptime across all 15 kiosks, enforced via vendor SLA with 48-hr response requirement. Spare units held in inventory to prevent service gaps at high-traffic sites.
02
Weekly Data Integrity Checks
Systematic review of usage logs, BAC ranges, and rideshare conversion rates. Anomalies trigger immediate vendor escalation. 100% data collection rate required for evaluation validity.
03
Vendor Compliance Standards
Vendor agreements mandate real-time uptime dashboards, API-accessible usage data, and proven maintenance history. Compliance verification is a zero-float critical path task.
04
Scalable Evaluation Framework
Pilot results feed a structured KPI report delivered Month 9. The framework is designed to support evidence-based expansion decisions and replication across other metro markets.
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS

## Slide 14
Key Findings & Recommendations
WHAT WE KNOW · WHAT WE RECOMMEND
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS
01
Cost Case Is Unusually Clear
$52,500 vs. $1.4M — a 97% cost advantage per prevented DUI tragedy. The social ROI model uses accepted NHTSA cost-of-crash valuation methodology, giving this figure institutional credibility. Lead with it in every investor and grant conversation.
02
Location Selection Is Everything
A kiosk at a bar exit outperforms one in a parking garage by 5× in BAC interactions — consistent with nudge theory: interventions closest to the decision point drive the highest behavioral change. Score all 15 sites on foot traffic, rideshare proximity, and BAC interaction potential.
03
Prioritize Vendor Data Capability
Hardware is commoditized. The program differentiator is real-time uptime dashboards, API data access, and rigorous data collection integrity — the evaluation framework only holds if the data infrastructure supports it. Vendor compliance verification is a critical path task, not an afterthought.
04
Launch Awareness Campaign on Day 1
The behavioral economics model only works if patrons know kiosks exist before their first encounter. Marketing must precede deployment — baseline DUI data is only valid when the choice environment is fully established from day one of operations.

## Slide 15
drinkwellleavebetter.com
UBER | LYFT | SD SAFETY | CA OTS
The Question Isn't Whether
We Can Afford This.
It's Whether We Can Afford
Another Year Without It.
90-day
launch target
15
kiosks deployed
$65K
total investment
$367K
net profit Y1
21×
min social ROI
97%
cost advantage
Total investment: $65,000 · 97% less than one preventable tragedy · Fully scalable model
SafeNight SD · drinkwellleavebetter.com · San Diego, California