COST ANALYSIS & VENDOR SELECTION

# 1. Budget Summary & Cost Structure

The total Year 1 budget for the SafeNight SD kiosk pilot is $65,000, covering hardware procurement, installation, maintenance, and program coordination across 15 kiosk units in San Diego. The table below provides the full cost breakdown with added detail on unit economics.

| Budget Category | Unit Cost | Units | Total Cost |
| --- | --- | --- | --- |
| Kiosk hardware (breathalyzer + enclosure + display) | $2,500 | 15 | $37,500 |
| Installation & site preparation (per kiosk) | $500 | 15 | $7,500 |
| Annual maintenance & SLA contract (per kiosk/yr) | $500 | 15 | $7,500 |
| Connectivity — cellular data plan per unit, 12 months | $0* | 15 | Vendor-bundled |
| Part-time program coordinator (10 hrs/wk × 12 months @ $24/hr) | N/A | 1 | $12,500 |
| Marketing & launch campaign | N/A | — | Sponsor-funded / $0 |
| Contingency reserve (5% of hard costs) | N/A | — | $2,625* |
| TOTAL YEAR 1 INVESTMENT | — | — | $65,000 |

*Cellular data is bundled in vendor SLA for qualifying bids. Contingency reserve of $2,625 is held within the $65K envelope and deployed only if an approved risk event materializes.

## 1.1  Unit Economics per Kiosk

| Metric | Year 1 (Pilot) | Year 2+ (Scaled) |
| --- | --- | --- |
| Hardware cost per kiosk | $2,500 | $2,200 (volume discount) |
| Installation cost per kiosk | $500 | $350 (efficiencies gained) |
| Annual maintenance per kiosk | $500 | $450 |
| Total all-in cost per kiosk (Year 1) | $3,500 | $3,000 |
| Coordinator cost allocated per kiosk | $833 | $500 (efficiency) |
| Total cost per kiosk including overhead | $4,333 | $3,500 |
| Revenue target per kiosk (to break even) | $4,333/yr | $3,500/yr |
| Revenue generated per kiosk (Year 1 projected) | $28,859 | $35,000+ |
| Return per kiosk (Year 1) | $24,525 surplus | $31,500+ surplus |

# 2. Revenue Projections

SafeNight SD generates revenue across five distinct streams, reducing reliance on any single source and creating a resilient financial model. The table below shows the Year 1 baseline projection.

| Revenue Stream | Basis | Year 1 Est. | Notes |
| --- | --- | --- | --- |
| Kiosk screen advertising (15 kiosks) | Ad partnerships | $180,000 | $1,000/kiosk/month; ramp-up pricing Q1 |
| Government grants (CA OTS / NHTSA 405d) | Grant awards | $150,000 | Applications filed Month 1; modeled as upside |
| B2B data licensing (anonymized BAC data) | Insurance / Research | $60,000 | Fully anonymized; CCPA-compliant; $5,000/mo |
| Bar venue SaaS subscriptions (15 venues) | Monthly fee/venue | $35,880 | $199/venue/month × 15 venues × 12 months |
| Rideshare referral commissions (Uber / Lyft) | Per-conversion fee | $7,000 | ~$0.75/booking; ~777 bookings/month est. |
| ESTIMATED YEAR 1 GROSS REVENUE | — | $432,880 | 5.7× revenue-to-cost ratio |
| ESTIMATED YEAR 1 NET PROFIT | — | $367,880 | After $65,000 total investment |

# 3. Bar Venue Subscription Model

The bar venue SaaS subscription is a recurring monthly revenue stream in which participating venues pay a fixed fee to host a SafeNight SD kiosk and receive data, reporting, and liability-reduction benefits in return. This section provides a full breakdown of the subscription structure, pricing tiers, value proposition, and revenue simulation.

## 3.1  Subscription Tier Structure

SafeNight SD offers three subscription tiers to accommodate venues of different sizes and engagement levels. All tiers include kiosk hosting; higher tiers unlock data analytics and co-branded marketing benefits.

| Tier | Monthly Fee | Annual Fee | Included Benefits |
| --- | --- | --- | --- |
| Starter | $99/mo | $1,188 | Kiosk hosting, basic uptime reporting, SafeNight SD co-branded signage at entry |
| Standard ★ | $199/mo | $2,388 | All Starter benefits + monthly BAC usage report, Uber/Lyft promo code allocation (50 codes/mo), inclusion in SafeNight SD venue directory |
| Premium | $349/mo | $4,188 | All Standard benefits + real-time dashboard access, 100 promo codes/mo, co-branded social media features, priority kiosk maintenance, quarterly DUI liability report for legal/insurance |

★ Standard tier is the baseline used in the Year 1 financial model. All 15 pilot venues are assumed to subscribe at the Standard tier.

## 3.2  Value Proposition for Bar Venues

Venues receive tangible financial and reputational benefits that justify the subscription cost:

- Liability reduction: documented evidence that the venue actively promotes responsible drinking, potentially reducing dram shop liability exposure

- Insurance premium negotiation: quarterly DUI liability report (Premium tier) can be presented to insurers as risk mitigation documentation

- Customer retention: Uber/Lyft promo codes keep patrons engaged with the venue's brand during the ride home

- Compliance edge: venues that can demonstrate DUI intervention programs are better positioned with city licensing authorities

- PR and marketing: SafeNight SD co-branding signals community responsibility — differentiates the venue in a competitive market

- Data insights: monthly BAC usage reports show peak hours, patterns, and customer behavior data for staffing and operations planning

## 3.3  Subscription Revenue Simulation by Tier Mix

The following simulation models Year 1 SaaS revenue under different assumptions about how the 15 pilot venues distribute across the three tiers.

| Scenario | Starter Venues | Standard Venues | Premium Venues | Monthly Rev. | Annual Rev. |
| --- | --- | --- | --- | --- | --- |
| Conservative (all Starter) | 15 | 0 | 0 | $1,485 | $17,820 |
| Baseline (all Standard) ★ | 0 | 15 | 0 | $2,985 | $35,820 |
| Optimistic Mix (5/5/5) | 5 | 5 | 5 | $3,235 | $38,820 |
| Upsell Scenario (3/7/5) | 3 | 7 | 5 | $3,387 | $40,644 |
| Premium Heavy (0/5/10) | 0 | 5 | 10 | $4,485 | $53,820 |
| Year 1 Model Used (Baseline ★) | — | 15 | — | $2,985/mo | $35,820 |

Note: The original financial model used $35,880 (rounding). Revised figure is $35,820 based on $199 × 15 × 12. Difference of $60 is immaterial to the overall financial case.

# 4. Sensitivity Analysis

## 4.1 Sensitivity Analysis — What Drives Profitability Most?

| Rank | Variable | Conservative | Optimistic | Δ Impact | Execution Risk |
| --- | --- | --- | --- | --- | --- |
| 1 | Government grant funding | $0 | $150,000 | +$150,000 | Medium |
| 2 | Advertising fill rate | $90,000 | $171,000 | +$81,000 | Medium |
| 3 | B2B data licensing | $0 | $60,000 | +$60,000 | High |
| 4 | SaaS subscription tier mix | $11,424 | $40,644 | +$29,220 | Low |
| 5 | Number of kiosks deployed | 12 units | 15 units | +$18,000 est. | Low |
| 6 | Rideshare commissions | $2,000 | $7,000 | +$5,000 | Low |

# 5. Social Return on Investment (Social ROI)

Social ROI quantifies the public health and safety value generated by SafeNight SD beyond the financial return. Using NHTSA's published cost-of-crash methodology (DOT HS 813 403), the program's social value can be estimated based on DUI incidents prevented.

| Scenario | DUI Incidents Prevented | Social Value Generated | Social ROI on $65K Investment |
| --- | --- | --- | --- |
| Conservative | 1 per year | $1,400,000 | 21.5× ($1.4M ÷ $65K) |
| Realistic | 3 per year | $4,200,000 | 64.6× ($4.2M ÷ $65K) |
| Optimistic | 10 per year | $14,000,000 | 215× ($14M ÷ $65K) |
| Combined Financial + Social ROI (Realistic) | 3 incidents | $4,567,820 | 70.3× total return on $65K |

Source: NHTSA Traffic Safety Facts — The Economic and Societal Impact of U.S. Motor Vehicle Crashes (DOT HS 813 403). Cost-per-crash includes medical, legal, emergency response, lost productivity, and quality-of-life impact.

# 6. Vendor Evaluation Matrix

Four vendors were evaluated against SafeNight SD's weighted criteria. The scoring model applies weightings based on the program's priority: hardware reliability is most critical for kiosk uptime; data/API capability enables the data licensing revenue stream; SLA quality protects the 95% uptime KPI.

## 6.1  Weighted Scoring Model

| Vendor | Hardware 30% | Data/API 25% | SLA 20% | Price 15% | Compliance 10% | Weighted Score |
| --- | --- | --- | --- | --- | --- | --- |
| BACtrack Solutions ★ Primary | 9/10 | 8/10 | 9/10 | 8/10 | 10/10 | 8.85 |
| AlcoHAWK Pro (Backup #1) | 8/10 | 7/10 | 8/10 | 9/10 | 9/10 | 8.00 |
| SmartStart Inc. (Backup #2) | 8/10 | 9/10 | 7/10 | 7/10 | 9/10 | 8.00 |
| KioskBrands Custom | 7/10 | 6/10 | 7/10 | 10/10 | 8/10 | 7.35 |

Weighted score calculation: (Hardware × 0.30) + (Data/API × 0.25) + (SLA × 0.20) + (Price × 0.15) + (Compliance × 0.10). BACtrack scores 8.85 — highest among all evaluated vendors.

## 6.2  Vendor Cost Comparison

| Vendor | Unit Price | 15-Unit Cost | Annual SLA | Year 1 Total (15 units) |
| --- | --- | --- | --- | --- |
| BACtrack Solutions | $2,500 | $37,500 | $7,500 | $45,000 + install |
| AlcoHAWK Pro | $2,200 | $33,000 | $8,250 | $41,250 + install |
| SmartStart Inc. | $2,800 | $42,000 | $6,000 | $48,000 + install |
| KioskBrands Custom | $1,950 | $29,250 | $9,000 | $38,250 + install |

BACtrack is not the cheapest option but delivers the highest weighted score. The $3,750 premium over AlcoHAWK is justified by superior hardware reliability (9 vs. 8) and full regulatory compliance (10 vs. 9), which directly protect the program's 95% uptime KPI and grant eligibility.

# 7. Vendor Requirements — Mandatory RFP Criteria

All vendors responding to the SafeNight SD Request for Proposals must satisfy the following criteria. Failure to meet any mandatory requirement results in automatic disqualification from the evaluation process.

| # | Mandatory Requirement | Verification Method | Linked KPI |
| --- | --- | --- | --- |
| 1 | Real-time uptime monitoring dashboard accessible by program coordinator | Live demo during evaluation | 95% uptime KPI |
| 2 | API-accessible usage data export (JSON or CSV format, minimum daily frequency) | API documentation review | Data licensing revenue |
| 3 | Proven deployment history: minimum 3 prior bar-district or public venue installations | Reference checks | Reliability assurance |
| 4 | SLA with maximum 48-hour on-site response for equipment failures | SLA document review | 95% uptime KPI |
| 5 | Single-use FDA-cleared mouthpieces with bulk supply contract | FDA clearance certificate | Hygiene & compliance |
| 6 | Cellular data connectivity bundled in contract (no third-party carrier required) | Contract term review | Cost containment |
| 7 | Compliance with California Department of Motor Vehicles breathalyzer accuracy standards | CA DMV certification | Legal compliance |
| 8 | Insurance certificate: minimum $2M general liability coverage | COI on file | Risk mitigation |
| 9 | Bar venue subscription support: vendor must provide co-branded reporting exports compatible with SaaS subscription tier deliverables | Sample report review | SaaS revenue stream |

# 7. References

18 sources that are publicly accessible to support our cost analysis are as follows:

1] Blincoe, L. et al. (2023). The Economic and Societal Impact of Motor Vehicle Crashes, 2019 (Report No. DOT HS 813 403). National Highway Traffic Safety Administration. The report places total U.S. crash costs in 2019 at $340 billion. URL: https://crashstats.nhtsa.dot.gov/Api/Public/ViewPublication/813403.pdf

[2] The total value of societal harm from motor vehicle crashes in 2019, which includes loss of life, pain, and decreased quality of life, was nearly $1.4 trillion — the figure SafeNight SD uses to calculate its Social ROI per prevented fatal DUI incident. URL: https://downloads.regulations.gov/NHTSA-2024-0100-0018/attachment_1.pdf

[3] NHTSA's National Center for Statistics and Analysis. (2025, May). Alcohol-Impaired Driving: 2023 Data (Report No. DOT HS 813 713). Of the 40,901 traffic fatalities in 2023, an estimated 12,429 people (30%) were killed in alcohol-impaired-driving crashes. The estimated economic cost of alcohol-impaired crashes was $58 billion. URL: https://crashstats.nhtsa.dot.gov/Api/Public/Publication/813713

[4] NHTSA's Advanced Impaired Driving Prevention Technology Report to Congress (2026) cites a comprehensive economic cost of approximately $14.1 million per fatality — supporting the per-incident Social ROI calculation used in the model. URL: https://www.nhtsa.gov/sites/nhtsa.gov/files/2026-03/Report-to-Congress-Advanced-Impaired-Driving-Prevention-Technology.pdf

[5] DUI arrests in the San Diego region totaled 2,269 for just the first six months of 2024, according to SANDAG's mid-year crime report — validating the 2,100+ annual arrest figure used in the project's problem statement. URL: https://mybailhotline.com/2024/10/san-diego-arrest-reason-stats/

[6] SANDAG. (February 2025). Arrests 2023: Law Enforcement Response to Crime in the San Diego Region. San Diego Association of Governments Criminal Justice Research Clearinghouse. URL: https://www.sandag.org/data-and-research/criminal-justice-and-public-safety/criminal-justice-research-and-clearinghouse

[7] City of San Diego Police Department. (2024). City of San Diego Annual Crime Report — January–December 2023. SDPD Data Transparency. URL: https://www.sandiego.gov/police/data-transparency/crime-statistics/annual-crime-reports

[8] California Office of Traffic Safety. Grants Program. Public entities are eligible to submit applications for OTS funding; 501(c)(3) nonprofits require a public entity as a grant host. Applications are submitted by January 31st through the Grants Electronic Management System. URL: https://www.ots.ca.gov/grants/

[9] In November 2025, the California OTS — through NHTSA — awarded a $2.2 million grant to the Los Angeles County District Attorney's Office for DUI and vehicular homicide prosecution and training, demonstrating the scale of active OTS grant disbursements in California. URL: https://da.lacounty.gov/media/news/los-angeles-county-district-attorneys-office-awarded-22-million-ots-grant-dui-and

[10] Governors Highway Safety Association. Section 405: National Priority Safety Program. All Section 405 programs are administered by NHTSA at the federal level and State Highway Safety Offices at the state level, each with its own eligibility criteria. URL: https://www.ghsa.org/resource-hub/section-405-national-priority-safety-program

[11] 23 CFR § 1300.23 — Impaired Driving Countermeasures Grants. Federal regulation governing NHTSA Section 405(d) grant eligibility, application requirements, and allowable uses of funds for impaired driving programs. URL: https://www.ecfr.gov/current/title-23/chapter-III/part-1300/subpart-C/section-1300.23

[12] Lyft. DUI Reductions. Across the U.S., rideshare has been associated with an 11.4% decrease in alcohol-involved fatal crashes. Research shows that when Lyft enters a market, ride volumes increase and DUI incidents decrease. URL: https://www.lyft.com/impact/dui-reductions

[13] Lyft's 2023 Economic Report found that 49% of Lyft riders are aged 18 to 34 — the demographic involved in nearly half of all alcohol-involved fatal crashes — and 63% of that group reported using Lyft when planning to drink. URL: https://www.lyft.com/blog/posts/has-rideshare-changed-bostons-drunk-driving-rates

[14] Conner, C.R. et al. (2021). "Association of Rideshare Use With Alcohol-Associated Motor Vehicle Crash Trauma." JAMA Surgery, 156(8):731–738. Rideshare volume had a significant negative correlation with motor vehicle trauma incidence, most evident in those under 30. URL: https://www.ncbi.nlm.nih.gov/pmc/articles/PMC8190695/

[15] DUI arrests decreased up to 53% after rideshare introduction in Boston, Worcester, and Northampton, MA, per a National District Attorneys Association study. Houston saw a 23.8% decrease in motor vehicle collision traumas on Friday/Saturday nights after Uber arrived. URL: https://www.makemyreceipt.com/reports/rideshare-transportation-expense-statistics

[16] BACtrack was founded in 2001 and received FDA marketing clearance in 2004. It was among the first companies to sell breathalyzers to the general public for personal use and has devices sold in over 20,000 stores and 25 countries worldwide. URL: https://en.wikipedia.org/wiki/BACtrack

[17] BACtrack S80 is DOT & NHTSA Approved and FDA 510(k) Cleared, using professional-grade fuel cell sensor technology. Independent agencies have tested popular personal breathalyzer brands and found BACtrack to be the most accurate. URL: https://www.amazon.com/BACtrack-Breathalyzer-Professional-Grade-Accuracy-Professional/dp/B0026IBZSK

[18] BACtrack Official Store. All Breathalyzers. Product catalog with specifications and pricing. URL: https://www.bactrack.com/collections/all-breathalyzers