MEETING 1 OF 3  ●  MINUTES OF MEETING

PROJECT KICKOFF MEETING

SafeNight SD — Topic Selection, Role Assignment & Scope Agreement

| Date: | Tuesday, February 18, 2026 |
| --- | --- |
| Time: | 5:00 PM – 7:00 PM (90 minutes) |
| Location: | CSUSM Library |
| Meeting Type: | Project Kickoff — First Group Meeting |
| Note-Taker: | Natasha |

# 1. Attendees

| Name | Role |
| --- | --- |
| Brenda | Project Manager |
| Clarisa | Project Manager |
| Natasha | Project Manager |

# 2. Purpose of the Meeting

This was the first official team meeting for the OM637 group project. The three team members — Brenda, Clarisa, and Natasha — met to agree on a project topic, assign roles, define the scope, and set ground rules for collaboration for the remainder of the semester.

Course Requirement (OM637) The group project requires the team to act as a Project Manager and produce: a scoped project plan, WBS, risk analysis, financial strategy, stakeholder analysis, and a 15–20 minute final presentation. All documentation must be maintained throughout the semester.

# 3. Topic Selection

## 3.1  Ideas Brainstormed

Each team member proposed one or two project concepts. The following were discussed:

| # | Proposed Idea | Proposed By | Team Reaction |
| --- | --- | --- | --- |
| 1 | Campus food waste reduction program | Natasha | Good cause; limited financial model |
| 2 | Breathalyzer kiosk network for San Diego bar districts | Clarisa | Strong ROI; clear problem; locally relevant — SELECTED |
| 3 | Smart parking system for downtown San Diego | Brenda | Saturated market; less differentiated |

## 3.2  Selected Topic

✔ Topic Selected — SafeNight SD A 15-kiosk breathalyzer and rideshare-integration network targeting San Diego's top entertainment districts. Selected unanimously by Brenda, Clarisa, and Natasha for its clear problem, quantifiable ROI, multi-stakeholder structure, and strong fit with all OM637 project deliverables.

Rationale agreed by all three members:

- Verifiable problem backed by NHTSA and CA OTS public data

- Clear hardware deliverables that map well to a WBS

- Multiple revenue streams enabling a realistic financial model

- Public-private partnership structure creates a rich stakeholder analysis

- Locally relevant to San Diego — professional and compelling for the presentation

# 4. Scope Agreement

## 4.1  In Scope

- 9-month pilot program designing deployment of 15 kiosks across San Diego

- Vendor selection process (RFP development and evaluation criteria)

- Site identification and venue MOU partnership strategy

- Full financial model: costs, revenue streams, Social ROI

- Risk register and mitigation planning

- Stakeholder identification and engagement strategy

- Quality and KPI evaluation framework

- All project management documentation for the professor

## 4.2  Out of Scope

- Actual procurement or execution of any real contracts

- Technical firmware development of the kiosk hardware

- Legal review of MOU or vendor contracts

- Full city-wide expansion beyond the 15-kiosk pilot

# 5. Team Norms & Communication

| Topic | Agreement |
| --- | --- |
| Primary communication | Group text thread — responses expected within 24 hours |
| File sharing | Google Drive shared folder — all drafts and final files saved here |
| Meeting cadence | Minimum 3 meetings: Kickoff, Design Review, and Presentation Day |
| Decision-making | Majority vote among the three; |
| Missed deadlines | Notify group 48 hours in advance; work redistributed if needed |
| Presentation rehearsal | One full run-through at least 1 week before presentation date |

# 6. Preliminary Work Breakdown

The following high-level work areas were agreed upon and assigned to team leads:

| Work Area | Lead | Target Completion |
| --- | --- | --- |
| Problem research — DUI stats, economic impact | Clarisa | February 25, 2026 |
| Solution design — kiosk workflow, placement strategy | Clarisa | March 1, 2026 |
| Project plan — WBS, timeline, critical path | Brenda | March 10, 2026 |
| Financial model — costs, revenue, ROI | Natasha | March 10, 2026 |
| Stakeholder analysis & MOU strategy | Natasha | March 10, 2026 |
| Risk register & mitigation planning | Brenda | March 10, 2026 |
| Presentation slides — design and build | All three members | April 10, 2026 |
| Project documentation (MOM, WBS doc, cost doc) | All three members | April 20, 2026 |

# 7. Action Items

| Action Item | Owner | Due Date | Status |
| --- | --- | --- | --- |
| Research San Diego DUI statistics and economic cost (NHTSA/CA OTS) | Clarisa | Feb 25, 2026 | Open |
| Research breathalyzer kiosk vendors and current market pricing | Clarisa | Feb 25, 2026 | Open |
| Draft initial project scope statement for team review | Brenda | Feb 25, 2026 | Open |
| Draft preliminary revenue model options (advertising, grants, SaaS) | Brenda | Mar 1, 2026 | Open |
| Identify potential bar/venue partners in Gaslamp, North Park, PB | Natasha | Mar 1, 2026 | Open |
| Research Uber/Lyft co-branded referral and partnership programs | Natasha | Mar 1, 2026 | Open |
| Create shared Google Drive folder and set up file naming convention | Brenda | Feb 20, 2026 | Open |
| Schedule Meeting #2 — target week of March 9, 2026 | All Three | Feb 22, 2026 | Open |

# 8. Next Meeting

Meeting #2 (Mid-Project Design Review) to be scheduled for the week of March 9, 2026. Each team member should arrive with their assigned research section completed. Agenda will cover: finalized WBS, solution design details, preliminary financial model, and the stakeholder map.