MEETING 2 OF 3  ●  MINUTES OF MEETING

MID-PROJECT DESIGN REVIEW

SafeNight SD — WBS Review, Financial Validation & Risk Planning

| Date: | Monday, March 16, 2026 |
| --- | --- |
| Time: | 6:00 PM – 8:15 PM (135 minutes) |
| Location: | MS Teams |
| Meeting Type: | Working Session — Design Review & Issue Resolution |
| Note-Taker: | Clarisa |

# 1. Attendees & Pre-Work Check-In

| Name | Role | Pre-Work Submitted? | Notes |
| --- | --- | --- | --- |
| Brenda | Project Manager | Yes — WBS draft + revenue model | Led session; presented financials |
| Clarisa | Project Manager | Yes — Vendor research + Risk register v1 | Took notes; presented vendor options |
| Natasha | Project Manager | Partial — Stakeholder list (power grid pending) | Action item assigned; MOU outline due |

# 2. WBS & Timeline Review

Brenda walked the group through the draft Work Breakdown Structure and project Gantt timeline for the 9-month pilot. The following items were reviewed, debated, and resolved by all three team members.

## 2.1  Phase Structure — Confirmed by All Three Members

| # | Phase | Timeline | Outcome After Review |
| --- | --- | --- | --- |
| 1 | Vendor Procurement | Month 1 (Apr–May 2026) | Confirmed — RFP approach agreed; Clarisa leads |
| 2 | Site Development | Month 2 (Jun 2026) | Confirmed — 20 candidate sites to score; Natasha leads outreach |
| 3 | Install & Deploy | Month 3 (Jul 2026) | Confirmed — 15 units; vendor installs; Clarisa oversees |
| 4 | Pilot Operations | Months 4–9 (Aug–Jan 2027) | Confirmed — 6-month live window; all three monitor KPIs |
| 5 | Evaluation | Month 9 (Feb–Apr 2027) | Confirmed — KPI report + expansion recommendation |

## 2.2  Open Issues Raised & Resolved

| Issue Raised By | Raised By | Resolution |
| --- | --- | --- |
| Is 3 months for installation too aggressive for 15 units? | Clarisa | Kept at Month 3; vendor delivery 4–6 weeks; parallel installs possible. Added spare unit buffer to risk plan. |
| Who owns compliance verification before vendor award? | Brenda | Assigned to Clarisa; CA DMV breathalyzer standards added as mandatory RFP requirement. |
| What happens if a kiosk underperforms its KPI targets? | Natasha | Added weekly data integrity review; vendor SLA must include 48-hr escalation path. |
| Should the financial model still work if grants are not awarded? | Brenda | Yes — advertising + SaaS subscriptions alone cover operating costs. Grant funding modeled as upside, not required. |

# 3. Financial Model Review

## 3.1  Cost Estimates — Validated

Brenda presented the draft cost model. Reviewed and approved by Clarisa and Natasha:

- Hardware cost per unit: Initially estimated at $3,000 — revised to $3,500 after Clarisa's vendor research confirmed current market pricing for fuel-cell breathalyzer kiosks

- Installation per site: $500/site confirmed reasonable based on comparable kiosk deployment case studies

- Part-time coordinator: $12,500/year (10 hrs/week at $24/hr) — agreed by all three and retained

- Total Year 1 investment confirmed at $65,000

## 3.2  Revenue Model — Debated & Refined

- Advertising revenue ($180,000): Natasha flagged this as optimistic for a pilot. Team agreed to keep as Year 1 target but note it as ramp-up revenue requiring advertiser sign-ups before launch

- Government grants ($150,000): Brenda confirmed CA OTS DUI grants exist; team agreed to focus on CA OTS and NHTSA Section 405d. Natasha to research application process

- B2B data licensing ($60,000): Clarisa raised privacy concern — confirmed all data is anonymized and aggregated; no PII involved. Natasha to note this in stakeholder communications

- Bar SaaS subscriptions ($35,880): Based on $199/month per venue for 15 venues; Natasha noted this must be included in the MOU terms

- Rideshare commissions ($7,000): Conservative estimate at $0.50–$1.00 per Uber/Lyft booking generated via QR code

Financial Consensus — Agreed by Brenda, Clarisa & Natasha Year 1 estimated gross revenue: $432,880 ¦ Total investment: $65,000 ¦ Net profit: $367,880 Social ROI (Conservative): 21× based on NHTSA valuation of $1.4M per prevented fatal DUI incident.

# 4. Risk Register Review

Clarisa presented Risk Register. All three members reviewed and adjusted ratings together. Two new risks were added during this session.

| Risk | Like. | Impact | Owner | Agreed Mitigation |
| --- | --- | --- | --- | --- |
| Vendor delays on hardware delivery | Medium | High | Clarisa | Pre-qualify 2 backup vendors during RFP; 2-week schedule buffer |
| Venue partner withdraws from MOU | Low-Med | Medium | Natasha | Maintain 5 alternate site options; flexible MOU exit clauses |
| Low public adoption of kiosks | Medium | High | Natasha | Pre-launch awareness campaign; Uber/Lyft promo codes as incentive |
| Equipment malfunction / downtime | Medium | High | Clarisa | 48-hr vendor SLA; spare units held at 2 high-traffic locations |
| Grant funding not awarded ★ NEW | Medium | High | Brenda | Model remains viable without grants; advertising + SaaS cover core costs |
| Negative public perception re: privacy ★ NEW | Low | Medium | Natasha | Emphasize fully anonymized data in all public-facing communications |

★ Two risks (grant funding not awarded, privacy perception) were added during this session — not present in v1.

# 5. Stakeholder Analysis Status

## 5.1  Stakeholders Confirmed by Natasha

- Government: California Office of Traffic Safety (CA OTS), SDPD, NHTSA

- Commercial Partners: Uber, Lyft, San Diego bar and venue owners

- Technology Vendors: BACtrack Solutions, AlcoHAWK Pro, SmartStart Inc.

- Community: San Diego residents, bar patrons, public health organizations

## 5.2  Outstanding Items (Action Items Assigned)

- Power/influence grid to be completed by Natasha before next meeting

- Engagement strategy per stakeholder tier (supporter, neutral, resistant) — Natasha

- MOU template outline to be drafted by Natasha by March 28, 2026

# 6. Presentation Planning

The team agreed on slide ownership for the final presentation. Full rehearsal set for April 16, 2026. All slides merged into one deck by April 10, 2026.

| Presentation Section | Owner | Notes |
| --- | --- | --- |
| Title slide & Agenda | Brenda | Keep to 1–2 slides |
| The Problem — DUI stats & gap in the system | Clarisa | Lead with the key numbers |
| Our Solution — kiosk design & workflow | Clarisa | Include how-it-works flow diagram |
| Project Methodology & Timeline (WBS + Gantt) | Brenda | Color-coded phase Gantt chart |
| Stakeholder Analysis & Partnership Model | Natasha | RACI + stakeholder register table |
| Financial Strategy & Social ROI | Brenda | Bar charts for revenue streams; ROI scenarios |
| Risk Analysis | Clarisa | Risk matrix with color coding |
| Quality Plan, Recommendations & Closing | Brenda | End with strong call to action |

# 7. Action Items

| Action Item | Owner | Due Date | Status |
| --- | --- | --- | --- |
| Update WBS with Phase 3 installation buffer note | Brenda | Mar 20, 2026 | Open |
| Complete vendor evaluation matrix — pricing from 3 vendors | Clarisa | Mar 25, 2026 | Open |
| Finalize revenue model — confirm bar SaaS at $199/month | Brenda | Mar 22, 2026 | Open |
| Add 2 new risks to register (grant funding, privacy concern) | Clarisa | Mar 18, 2026 | Open |
| Complete stakeholder power grid + draft MOU template outline | Natasha | Mar 28, 2026 | Open |
| Research CA OTS and NHTSA grant application requirements | Natasha | Mar 28, 2026 | Open |
| Draft assigned slides — rough content, no final design yet | All Three | Apr 5, 2026 | Open |
| Merge all slides into master deck; check for consistency | Brenda | Apr 10, 2026 | Open |
| Full presentation rehearsal — time each presenter, peer feedback | All Three | Apr 16, 2026 | Open |

# 8. Parking Lot

- Brand name confirmed: 'SafeNight SD' and tagline 'Drink Well. Leave Better.' — agreed by all three members.

- CCPA compliance for anonymized BAC data: noted as out of scope for this project plan; flagged as a post-pilot legal review item (Brenda to add a note in Recommendations slide).

- Scalability question: Brenda to prepare one-sentence expansion note in case professor asks about scaling to Los Angeles.

# 9. Next Meeting

Meeting #3 is the Final Presentation Day — Thursday, April 24, 2026 as part of the OM637 class session. No additional team meetings scheduled unless rehearsal on April 16 reveals gaps requiring another session. Brenda will send a final reminder via group text on April 22.