MEETING 3 OF 3  ●  MINUTES OF MEETING

FINAL PRESENTATION DAY

SafeNight SD — OM637 Group Project Presentation & Debrief

| Date: | Thursday, May 30th 2026 |
| --- | --- |
| Time: | Class session — approx. 3:10 PM start |
| Location: | California State University San Marcos — OM637 Classroom |
| Meeting Type: | Final Group Project Presentation & Post-Presentation Debrief |
| Presenter: | Brenda (primary), Clarisa, Natasha (shared sections) |
| Note-Taker: | Brenda (post-presentation debrief notes) |

# 1. Attendees

| Name | Role |
| --- | --- |
| Brenda | Project Manager |
| Clarisa | Project Manager |
| Natasha | Project Manager |
| Course Instructor (Professor) & Classmates | Faculty Evaluator |

# 2. Presentation Summary

Brenda, Clarisa, and Natasha delivered the SafeNight SD group presentation to the OM637 class. The following is a summary of each section presented.

## 2.1  The Problem — Presented by Clarisa

- Presented key DUI statistics: 2,100+ arrests annually in San Diego County; $487M annual economic cost

- 30% of San Diego crashes are alcohol-related and preventable with early intervention

- Identified the critical gap: no infrastructure exists at the decision point when someone leaves a bar

- Highlighted urgency: every hour without an intervention system costs approximately $55,600 in DUI-related economic damage

## 2.2  Our Solution — Presented by Brenda

- Proposed 15 self-service breathalyzer kiosks at bar exits, transit hubs, and entertainment districts

- Kiosk workflow: BAC test in under 10 seconds, color-coded result (green/amber/red), QR code to Uber/Lyft with promo code

- Target locations: Gaslamp Quarter, North Park, Pacific Beach, downtown transit stations, and major event venues

- Behavioral economics framework: kiosks positioned at the exact moment the drive-or-ride decision is made

## 2.3  Project Methodology & Timeline — Presented by Brenda

- 5-phase project plan over a 9-month pilot (April 2026 – April 2027) presented with Gantt chart

- Phase 1: Vendor Procurement; Phase 2: Site Development; Phase 3: Install & Deploy; Phase 4: Pilot Operations; Phase 5: Evaluation

- KPIs established: 25+ BAC tests/kiosk/day, 95%+ device uptime, 100% data collection rate

- Critical path milestones identified: Vendor Selection (June 1), Operational Readiness (August 4)

## 2.4  Stakeholder Analysis — Presented by Natasha

- Presented stakeholder register including CA OTS, SDPD, NHTSA, Uber, Lyft, bar owners, and the community

- Power/influence grid shown: CA OTS and bar venue owners identified as highest influence stakeholders

- Engagement strategy: government partners (monthly reporting), rideshare providers (monthly KPI data), bar venues (weekly check-ins)

- MOU structure outlined: venue subscriptions at $199/month in exchange for kiosk installation and data access

## 2.5  Financial Strategy & Social ROI — Presented by Natasha

- Total Year 1 investment: $65,000 ($52,500 hardware + $12,500 coordinator)

- Estimated Year 1 gross revenue: $432,880 across 5 streams

- Net profit Year 1: $367,880 — 5.7× revenue-to-cost ratio

- Social ROI presented in 3 scenarios: Conservative 21× ($1.4M / 1 DUI prevented); Realistic 64× (3 incidents); Optimistic 215× (10 incidents)

- Investor breakeven timeline: bar owners Week 1, government/grant funders Month 1–2

## 2.6  Risk Analysis — Presented by Natasha

- Four primary risks presented: vendor delays, venue withdrawal, low adoption, equipment malfunction

- Two secondary risks added during team review: grant funding not awarded, negative privacy perception

- Each risk presented with likelihood, impact, owner, and mitigation plan

- Mitigation highlights: secondary vendor shortlist, 5 backup site locations, pre-launch marketing campaign, 48-hour vendor SLA

## 2.7  Quality Plan & Recommendations — Presented by Natasha, Clarisa

- Quality standards: 95% uptime SLA, weekly data integrity checks, vendor compliance verification as critical path task

- Evaluation framework: KPI report delivered Month 9 to support expansion decision

- Four key recommendations: lead with the $65K vs. $1.4M cost argument; prioritize location scoring; vendor data capability over hardware cost; launch marketing before kiosks go live

# 3. Post-Presentation Debrief (Team Only)

Following the class session, Brenda, Clarisa, and Natasha held a brief debrief to capture lessons learned and confirm any remaining documentation tasks.

## 3.1  Areas for Improvement

- Recommendations slide need to add more pictures instead of text

- Need to consider privacy policy

# 4. Final Documentation Checklist

The team confirmed the following documentation deliverables to be submitted to the professor:

| Document | Owner | Status |
| --- | --- | --- |
| MOM #1 — Project Kickoff (February 18, 2026) | Natasha | Complete |
| MOM #2 — Mid-Project Design Review (March 16, 2026) | Clarisa | Complete |
| MOM #3 — Final Presentation Day (April 24, 2026) | Brenda | Complete |
| Research & Related Articles | Clarisa | Complete |
| Cost Analysis & Vendor Selection | Brenda | Complete |
| Work Breakdown & Team Responsibilities | All Three | Complete |
| Final Presentation Slide Deck (SafeNight SD) | All Three | Complete — submitted |

# 5. Project Close

Project Status: COMPLETE The SafeNight SD OM637 group project has been successfully delivered. All presentation and documentation deliverables are complete. Brenda, Clarisa, and Natasha formally close out the project as of April 30, 2026.