WORK BREAKDOWN & TEAM RESPONSIBILITIES

SafeNight SD — WBS, Role Assignments & Contribution Log

# 1. Work Breakdown Structure (WBS)

The SafeNight SD project is organized into 5 phases. Each phase contains discrete work packages assigned to specific team leads.

| Phase 1 — Vendor Procurement ¦ Month 1 ¦ Lead: Procurement Lead |  |  |  |
| --- | --- | --- | --- |
| WP# | Work Package | Owner | Duration |
| 1.1 | Develop & Issue RFP | Procurement Lead | 4/27 – 5/1 (3 days) |
| 1.2 | Vendor Review Period | All Team Members | 5/4 – 5/15 (8 days) |
| 1.3 | Bid Evaluation & Scoring | Procurement + PM | 5/18 – 5/22 (3 days) |
| 1.4 | Compliance Verification | Operations Lead | 5/25 – 5/29 (3 days) |
| 1.5 | Vendor Selection & Award | Project Manager | 6/1 – 6/1 (1 day, CRITICAL) |
| 1.6 | Contract Negotiation & Signing | PM + Procurement Lead | 6/2 – 6/8 (5 days) |

| Phase 2 — Site Development ¦ Month 2 ¦ Lead: Site Development Lead |  |  |  |
| --- | --- | --- | --- |
| WP# | Work Package | Owner | Duration |
| 2.1 | Candidate Location Scoring | Site Development Lead | 5/4 – 5/15 (8 days) |
| 2.2 | Physical Site Walkthroughs | Site + Operations Lead | 5/18 – 5/29 (8 days) |
| 2.3 | Venue Outreach & MOU Drafting | Partnership Lead | 6/1 – 6/26 (18 days) |
| 2.4 | MOU Signing & Site Confirmation | PM + Partnership Lead | 6/29 – 7/3 (3 days) |

| Phase 3 — Install & Deploy ¦ Month 3 ¦ Lead: Operations Lead |  |  |  |
| --- | --- | --- | --- |
| WP# | Work Package | Owner | Duration |
| 3.1 | Kiosk Hardware Delivery & Receiving | Operations Lead | 7/7 – 7/11 (5 days) |
| 3.2 | Physical Installation at All 15 Sites | Vendor + Operations Lead | 7/14 – 7/25 (10 days) |
| 3.3 | Connectivity & API Integration Testing | Technology Lead | 7/28 – 8/1 (5 days) |
| 3.4 | Operational Readiness Sign-Off | Project Manager | 8/4 – 8/4 (1 day, CRITICAL) |

| Phase 4 — Pilot Operations ¦ Months 4–9 ¦ Lead: Project Manager |  |  |  |
| --- | --- | --- | --- |
| WP# | Work Package | Owner | Duration |
| 4.1 | Staff & Coordinator Training | Operations Lead | Aug 4 – Aug 8 |
| 4.2 | Marketing Launch & Public Awareness Campaign | Marketing Lead | Aug 11 onward |
| 4.3 | Live Operations & Weekly Monitoring | All Leads | Aug – Jan 2027 |
| 4.4 | Monthly KPI Reporting to Stakeholders | PM + Financial Lead | Monthly |

| Phase 5 — Evaluation ¦ Month 9 ¦ Lead: All Team Members |  |  |  |
| --- | --- | --- | --- |
| WP# | Work Package | Owner | Duration |
| 5.1 | Data Compilation & KPI Analysis | Financial + Tech Lead | Feb – Mar 2027 |
| 5.2 | Pilot Evaluation Report | Project Manager | March 2027 |
| 5.3 | Expansion Recommendation to Stakeholders | All Team Members | April 2027 |

# 2. Team Role Assignments

| Team Member | Role / Title | Primary Responsibilities |
| --- | --- | --- |
| Brenda | Project Manager & Financial Lead | Overall project oversight, stakeholder communication, milestone tracking, vendor selection final approval, budget management, revenue model, grant applications, monthly KPI reporting |
| Clarisa | Operations, Vendor & Risk Lead | RFP development, vendor evaluation, installation oversight, maintenance coordination, uptime monitoring, risk register maintenance, quality plan execution, vendor SLA compliance monitoring, data integrity reviews |
| Natasha | Partnership & Marketing Lead | Venue outreach, MOU drafting, Uber/Lyft integration, awareness campaign, stakeholder engagement, stakeholder register, marketing plan development |

# 3. Contribution Summary

Each team member contributed to the presentation and documentation as follows:

| Team Member | Presentation Sections | Documentation Sections |
| --- | --- | --- |
| Brenda | Title & Agenda, Project Methodology & Timeline, Financial Strategy & Social ROI Analysis, Quality Plan & Recommendations | Minutes of Meeting (MOM #3), Work Breakdown Structure (WBS), Cost Analysis & Budget Document, Grant Research |
| Clarisa | The Problem (DUI Statistics), Our Solution (Kiosk Design & Workflow), Risk Analysis, Kiosk Technology & Project Timeline | Minutes of Meeting (MOM #2), Vendor Evaluation Matrix, WBS Work Packages, Risk Register, Quality Plan, Research Articles |
| Natasha | Stakeholder Analysis, Partnership Model, Agenda Slide | Minutes of Meeting (MOM #1), Stakeholder Register, MOU Template, Marketing Plan |